Assignment Cover Sheet

| Student Name: | Mudingase Zulu |
| --- | --- |
| Student Number: | 1164 |
| Course: | Events Management |
| Assignment NO: | Fourteen (14) |

Student Statement:

By submitting this assignment, I confirm that this is my own work.

| Student Signature | Mudingase Zulu | Date | 13 November 2014 |
| --- | --- | --- | --- |

For Tutor / Assessor Use Only

| Total Marks |  |
| --- | --- |
| Marks Obtained |  |
| Percentage / Grade |  |

Mundingase  Zulu St 1164: Events Management: Assignment 14

Q I .Which type of waste is usually accumulated at most large events?

Ans. The following is usually waste accumulate at most large events:

- waste water from toilets; showers and hand-washing basins and food concessions

- paper and cardboard packaging;

- food and drink containers;

- left-over food debris;

- waste food from food concessions;

- glass; plastics; metal can and other  metal waste

- human waste products i.e vomit;

- medical waste such as needles and bandages;

- remains of camp fires;

Q ii. Outline the main hazards posed by waste at events.

Ans.  The following are hazards posed by waste at events:

Cuts, grazes needle stick injuries to workers during collection and removal of waste

- Infections arising from back strains due to manual handling.

- blocking emergency access routes if remain uncollected and tripping

hazards to the audience;

- Fire hazard may occur when waste is ignited

- Attraction of insects particularly housed fly and rodents in Africa.

- Movement of garbage collection vehicles within event premises..

- Children may play around with wastes such as empty water bottles and canes.

iii. If you are to manage workers and equipment at a large outdoor event,

which areas will you pay special attention for waste collection when appointing staff?

Ans.  If  I am to  manage  workers and equipment at a large outdoor event, I would pay attention to places where waste would be generated the most such as following areas::

- Approaches to event site such as surrounding streets or land;

- Entrances and exits;

- Arenas and stages;

- Sanitary areas such as wash places and toilets

- Service point areas such as first-aid health care areas, catering and restaurant  areas as well as

- Camping area

Q.2. Prepare a waste management plan for an outdoor event that will contain foodstalls and will be attended by approximately 10,000 people. (6

Answer.

Waste Management Plan for Out Door Event.

2.1 Event Details

| Name of Events: | Zambia National Agricultural and Commercial Show |
| --- | --- |
| Dates: | 3 December 2014 to 6 December 2014 (4days) |
| Time | 8.00 hrs to 17:00hrs daily |
| Address of Venue | Plot 100 Great East Road, Lusaka |
| Anticipated crowd size: Event activities: | 8,000 |
| Venue description: | Open arena |
| Venue crowd capacity: | 10,000 |
| Existing facilities: | Site meeting rooms, permanent sanitary facilities, electricity, running water, access road, wire fenced, 6 gates entry and 6 exit gates |
| Other relevant information | Accessed by tarred road and public transport. Foreign investors will be in attendance. |

2.2 Catering

| Food or Drink | Packaging or Table ware | Material type |
| --- | --- | --- |
| Nsima (hard Porridge) | Polyether bags Enamel plates | Plastic and paper |
| Beef and meet products, vgetables | Paper bags, plastic bags | Plastic paper |
| Spices | Bottles, bags, plastic bags | Glass bottles |
| Cooking oil | Plastic contianers | plastic |
| Chips | Paper bags and plastic cup | Paper bag and plastic bags |

2.3 Activity waste

| Stall Type | Waste type |
| --- | --- |
| Burger boss |  |
| Mamas restaurant | Food craps, card boxes |
| Bowas Traditional foods | Paper, food craps, card board boxes |

2.4 Catering Wastes

| Stall Type | Waste type |
| --- | --- |
| Burger boss |  |
| Mamas restaurant | Food craps, card boxes |
| Bowas Traditional foods | Paper, food craps, card board boxes |

2.5  . Waste Generation and Quantities

| What | Where | How much | When |
| --- | --- | --- | --- |
| Food scraps card boxes | Catering areas (Mamas, bowas, burger and boss) | Very large quantities | Before, during and after the event |
| Card boxes | Mamas, bowas, burger boss and entry points | Very large quantities | Before, during and after the event |
| Paper | Mamas, bowas, burger boss, entry, main arena | Very large quantities | Before, during and after the event |
| Plastics | Mamas, bowas, burger boss, entrance, exit gates and catering areas | Very large quantities | Before, during and after the event |
| Polythene bags | Mamas, bowas, burger boss | Very large quantities | Before, during and after the event |
| Bottles | Mams restaurant, entry, exit | Very large quantities | Before, during and after the event |
| waste water from toilets; showers and hand-washing basins; | Mamas, Bowas, Burger boss, entrance, exit gates and catering areas-mainly sanitary areas | Very large quantities | Before, during and after the event |

2.6   Waste Stations (what for, how many)

Waste station to allow a proper management of waste and minimize risks associated with its accumulation and indiscriminate disposal.

Ten (30) waste stations designated at the 10 catering centers, five (5) the entrance, exit and  five (5) at the main arena and the other Ten  (10) along walk ways within the event premises.

  - Waste Station locations (where, when)

Waste station will be locates at catering centers, entrance and exit stations and points along walk ways this should be done before the event. other locations may be created depending on need.

2.8 . Promotion of waste system/handling (how announced, by whom)

| ACTION | WHO | DONE (Tick) |
| --- | --- | --- |
| Write media release & issue to local media | Mudingase- Event Manager |  |
| Arrange for signage (translations if necessary) | Zulu-Technical office |  |
| Educate stallholders of waste system via presentation/flyer/phone | Mudingase-Event Manager |  |
| Script announcements for PA or Master of Ceremonies | Musaope Event coordinator |  |
| Develop competition | Mudingase-Event Manager |  |
| Include waste minimization initiatives in advertising feature of event | Musaope- Event coordinator |  |
| Arrange for local Council, community group, waste board stall to promote recycling at event/public education | Musaope Event coordinator |  |

2.9 Activities required before the event

| ACTION | BY WHOM | BY WHEN | DONE (Tick) |
| --- | --- | --- | --- |
| Order bin caps | Musaope- Event coordinator | 15 Janaury 2014 |  |
| Obtain labels | Zulu-Technical office | 7 February 2014 |  |
| Arrange for collection of bin caps | Zulu-Technical office | 10 February 2014 |  |
| Empty existing bins before event | Zulu-Technical office | 1 December 2014 |  |
| Remove standalone garbage bins | Mudingase-Event Manager | 1 December 2014 |  |
| Cover up existing bins | Musaope-Event coordinator | 4 December 2014 |  |
| Set up waste stations at predetermined location | Musaope Event coordinator | 1 December 2014 |  |
| Link/bind waste station bins together | Zulu-Technical office | 4 December 2014 |  |
| Check on bin location & signage | Musaope- Event coordinator | 2 December 2014 |  |
| Arrange packaging plan | Mudingase - Event Manager | 15 February 2014 |  |

2.10. Waste management during the event

| ACTION | BY WHOM | DONE (Tick) |
| --- | --- | --- |
| Monitor set up waste performance | Musaope-Event coordinator |  |
| Educate/remind stallholders as necessary | Zulu-Technical office |  |
| Master of Ceremonies read announcements | Chisomo-Master of ceremony |  |
| Monitor waste & recycling bin content and quantities | Mudingase-Event Manager |  |
| Arrange bin cleaning/collection schedule | Mudingase-Event Manager |  |
| Empty existing bins before event | Musaope- Event coordinator |  |
| Remove standalone garbage bins | Musaope Event coordinator |  |
| Cover up existing bins | Zulu-Technical office |  |
| Set up waste stations | Musaope- Event coordinator |  |
| Link/bind waste station bins together | Zulu-Technical office |  |

11. Waste Management after the event (by whom, by when)

| ACTION | BY WHOM | BY WHEN | DONE (Tick) |
| --- | --- | --- | --- |
| Empty bins after event | Zulu-Technical office | 7 December 2014 |  |
| Bring back and put in place standalone garbage bins | Mudingase-Event Manager | 7 December 2014 |  |
| Cover up bins | Musaope-Event coordinator | 7 December 2014 |  |
| Remove signage | Musaope- Event coordinator | 7 December 2014 |  |
| Arrange transportation of bins | Mudingase - Event Manager | 7 December 2014 |  |
| monitor bin cleaning/collection schedule | Mudingase-Event Manager | 7 December 2014 |  |

12. Contact List (who, phone number, and area of responsibility)

| WHO | PHONE | AREA OF RESPONSIBILITY |
| --- | --- | --- |
| MR Morgan Kalembo | 20976752862 | Fire, Health and Safety |
| MR. Oswald Bulawayo | 20977675787 | Waste Management |
| Mr. Zacchaeus Mulumbu | 20967022872 | Security |
| Chapman Lungu | 20999938919 | Recycling Center |
| Ms. Gladys Banda | 20979 951819 | Bin and labels |
| Mr. Levison N’gwane | 20977694620/ | Graphic artist |
| Ms Bridget Malaki | 20977897754 | Back –up power suppliers/ Generator services |
| Mr. Jones daka | 20979313424 | Red cross/First AID |
| Ms. Mlawo Nkopma | 20977 – 775518 | Licensing office-local council |

13. Performance Review:

- Date of performance review

- List of attendance

- Select recorder of review meeting

14. Attachment(s)

- Attach the following

- All planning and review meeting minutes

- Contact details of  venders and supplirs that were involved

- Phone interviews,

- Stallholder responses)

Q.3. According to the personal protective equipment Regulation 1992 what are thesuitable protective clothing and equipment’s for people working on wasteremoval? And who is responsible for providing these items to the staff?

According to the personal protective equipment Regulation 1992, suitable clothing and equipment for people waste removal include the following:

- protective boots or shoes

- trousers and jackets;

- waterproof suits;

- fluorescent waistcoats;

- hard hats;

- goggles;

- Gloves

Waste contractors are responsible for providing these protect cloths and equipment  to staff.