Assignment Cover Sheet

| Student Name: | Raymond Harrison |
| --- | --- |
| Student Number: | 1582 |
| Course: | Diploma in project management level 4 |
| Assignment NO: | 1 |

Marking Criteria:

We expect the learners to write minimum one well expressed point in three lines against each allocated mark. This means one needs to write 15 lines with 5 well expressed points to get high grades for a 5 marks question.

For high grades use examples and illustrations where appropriate.

Please insert your completed assignment ( in word format) here: Q: 1: Multiple Choice Questions: I. What are the five project management process groups, in order? d) Initiation, Planning, Executing, Controlling, and Closing II. A project is considered successful when: d) The project meets or exceeds the expectations of the stakeholders. III. You are the project manager for a large construction project. The project objective is to construct a set of outbuildings to house the Olympic support team that will be arriving in your city 18 months from the project start date. Resources are not readily available as they are currently assigned to other projects. Jack, an expert crane operator, is needed for this project two months from today. Which of the following skills will you use to get Jack assigned to your project? a) Negotiation and influencing skills IV. The amount of authority a project manager possesses can be related to: d) The project manager’s influencing skills V. Your company manufactures small kitchen appliances. They are introducing a new product line of appliances in designer colours with distinctive features for kitchens in small spaces. These new products will be offered indefinitely starting with the spring catalog release. Which of the following is true? c) This is an ongoing operation because the new product line will be sold indefinitely. It’s not temporary. Q: 2: Shorts Questions: I. What is the difference between a project and routine work? A project differs from routine work in the fact that it is a one time thing, its has a definitive start and finish, where as routine work is on going II. Briefly outline the tasks that a project manager performs during the course of his project. Planning and defining scope Activity planning and sequencing Resource planning Developing Schedules Time estimating Cost estimating Developing a budget Documentation Creating charts and schedules Risk analysis Managing risks and issues Monitoring and reporting progress Team leadership Strategic Influencing Business partnering Working with vendors Scalability, Interoperability and Portability analysis Controlling quality Benefits realisation III. Describe different stages of the project life cycle. Initiating – Project objective or need is identified Planning – Steps needed to meet the projects objectives or needs are planned Executing – Project plan is implemented and put into action Controlling – Progress is monitored and any adjustments or variations are made Closing – handing over the project and releasing the final deliverables to the customer/business IV. Outline the key skills every good project manager should possess. Communication skills Organizational skills Budgeting skills Problem solving Negotiation and influencing Leading Team building and human resources Industry knowledge V. It is said that there are five process groups and nine knowledge areas in project management. Name all the process groups and knowledge areas. Process Groups; initiation process planning process executing process monitoring and controlling process closing process Knowledge Areas; project integration management project scope management project time management project cost management project quality management project human resources management project communications management project risk management project procurement management Activity: Use this activity to define the key activities of a project within your organisation. 1 Select a project that you have been involved in or affected by during the past year. 2 Identify what the different stages were, and approximately how long each lasted. 3 Note down the key activities of each stage. Project title: Engineers Bar, Christchurch – Electrical installation Stage; Length of time; Key activities. Tender stage (initiation); 9 days; Receive and review drawings and specification, Cost estimating, Getting quotes from wholesalers Getting quotes from sub contractors Comparing and evaluating prices Producing a tender letter and final price. Acceptance (planning); 3 weeks; Receiving written acceptance of our tender price Signing contracts with builders Ensuring all insurances are up to date and in place Writing site specific safety plans Writing task analysis Choosing a site forman (team leader) Choosing a project team. Creating a time management GANT chart Ordering materials. Construction (execution); 10 weeks; Delivery of materials to site 1st fix (installation of containment and cables) 2nd fix (fitting of light fittings, sockets and switches). Construction (control); 10 weeks; Site meetings with main contractors & sub trades Tool box talks with project team. Pricing and submitting any variations Electrical testing at the end of the 1st fix stage Electrical testing at the end of the 2nd fix stage Final testing and commissioning. Hand Over (closing); 3 weeks; Final walk through on site with the client Producing As-Built drawings Producing Operations and Maintenance manuals Submitting final claim for payment and variations Meeting with forman to discuss projects success.

Student Statement:

By submitting this assignment, I confirm that this is my own work.

| Student Signature | Raymond Harrison | Date | 1/11/2015 |
| --- | --- | --- | --- |

For Tutor / Assessor Use Only

| Total Marks |  |
| --- | --- |
| Marks Obtained |  |
| Percentage / Grade |  |