Assignment Cover Sheet

| Student Name: | Noel Catubig Tuazon |  |
| --- | --- | --- |
| Student Number: | 1762 |  |
| Course: | International Diploma in Project Management level 4 |  |
| Assignment NO: | 11 |  |

Marking Criteria:

We expect the learners to write minimum one well expressed point in three lines against each allocated mark. This means one needs to write 15 lines with 5 well expressed points to get high grades for a 5 marks question.

Please insert your completed assignment ( in word format) here: Date ; July 23 2016 ASSESMENT 11 1. Give short answers for the following questions: i. Which processes are involved in project risk management? ANSWER ; Project Risk Management contains six processes: Risk Management Planning, Risk Identification, Qualitative Risk Analysis, Quantitative Risk Analysis, Risk Response Planning, and Risk Monitoring and Control . These processes are concerned with identifying and planning for potential risks that may impact the project. Organizations will often combine several of these processes into one step. For example, Risk Identification, Quantitative Risk Analysis, and Qualitative Risk Analysis might be performed at the same time. The important point is to strive to identify all the risks and develop responses to those with the greatest consequences for the project objective. ii. Define the term ‘risk holder’s tolerance.’ ANSWER ; Stakeholders will have differing tolerances of risk, depending on the project, the conditions, and the potential for loss or reward. Stakeholders’ risk tolerance may be known at the launch of the project, by their actions during the project, or through written policy statements. Consider a project to install new medical equipment in a hospital: there is little room for acceptance of errors because life and death are on the line. No short-cuts or quick fixes are allowed. Now, consider a project to create a community garden. Not only are life and death not on the line in the garden project, but the acceptance of risk is also different. The utility function is a person’s willingness to accept risk. The time and money costs required to eliminate the chance of failure are in proportion to the stakeholders’ tolerance of risk on the project. The cost of ensuring that there are no threats must be balanced with the confidence that the project can be completed without extraordinary costs. Iii. What is risk identification? ANSWER ; The risk management plan is one of the key inputs to the risk identification process. It describes how the risks will be identified, the overall management of the risk response process, and requirements for risk analysis. The risk management plan does not include the actual responses to the risks but, rather, the approach to the management of the process. There are several other inputs to the risk identification process other than the risk management plan. ** Identifying Risks “ After completing the risk management plan, it is time to start identifying the risks that may hinder the project’s success. Risk identification is the process of identifying the risks and then documenting how their presence may affect the project. Risk identification is an iterative process and can be completed by the project manager, the project team, a risk management team, and even SMEs. In some instances, stakeholders and even people outside the project may complete additional waves of risk identification . iv. Define the term ‘Qualitative Risk Analysis.’ ANSWER ; Qualitative risk “qualifies” the risks that have been identified in the project. Qualitative risk analysis is a broad approach to ranking risks by priority, which then guides the risk reaction process. Specifically, qualitative risk analysis examines and prioritizes the risks based on their probability of occurring and the impact on the project should the risks occur. Once risks have been identified and prioritized, qualitative risk analysis can lead to more in-depth quantitative risk analysis or move directly on to risk response planning. Preparing for Qualitative Risk Analysis : The first input to qualitative risk analysis is the risk management plan. The plan will dictate the process, the scoring model for identified risks, and the methodologies to be used. In addition to the risk management plan, the identified risks, obviously, will need to be analyzed. These are the risks that will be scored and ranked based on their probability and impact. The status of the project will also affect the process of qualitative risk analysis. The status of the project is linked to the time available for analyzing and studying the risks. There may be more time early in the project, while a looming deadline near the project’s end may create a sense of urgency to find a solution for the newly identified risks. Early in the project, there may be several risks that have not yet surfaced. Later in the project, new risks may become evident and will have to pass through qualitative analysis. Early in the project, there may be several risks that have not yet surfaced. Later in the project, new risks may become evident and will have to pass through qualitative analysis. The project type also has some bearing on the process. A project that has never been done before, such as the installation of a new technology, has more uncertainty than projects that have been carried out many times within an organization. First-time projects have limited resources on which to build a risk hypothesis, while recurring projects can rely on historical information. The accuracy and source of the data must be evaluated to determine the level of confidence in the identified risks. All risks are based upon some form of belief, proof and data. A hunch that an element is a risk is not as reliable as historical information, measured statistics, or expert knowledge that an element is a risk. The data precision is in proportion to the reality of the risk. A predetermined scale of probability and impact must be in place before risk analysis is carried out. Multiple scales are available to a project manager, but generally these should be in alignment with the risk management plan. The scale identified by the performing organization should be used if the performing organization has a risk management model. Finally, the assumptions used in the project must be revisited. During the risk identification process, the project team identifies and documents the assumptions used within the project. These assumptions will be evaluated as risks to the project’s success. * Completing Qualitative Analysis : While some risks demand attention, not all risks are worth responding to. Qualitative analysis is a subjective approach to prioritizing and organizing risks. Through a methodical and logical approach, the identified risks are rated according to probability and potential impact. The outcome of the ranking determines four things: ** It identifies those risks that are not critical, project-stopping risks, but that must still be documented. ** It identifies the risks that must be subjected immediately to risk response planning. ** It identifies the risks that require additional analysis through quantitative risk analysis. ** It prioritizes risks. * Examining the Results of Qualitative Risk Analysis ; Qualitative risk analysis takes place throughout the project. The project manager should route the risks through the qualitative risk analysis process as new risks become evident and identified. The end results of qualitative risk analysis are as follows: ** Overall risk ranking of the project: The overall risk ranking of the project allows the project manager, management, customers, and other interested stakeholders to comprehend the risk, the nature of the risk, and the condition between the risk score and the likelihood of success for a project. The risk score can be compared to other projects to determine allocation of talent to a project, prioritization, project selection, the creation of a benefit-cost ratio, or even the cancellation of a project because it is deemed too risky. ** Prioritized risks: The risks in the project can be prioritized by their score, their ranking of high, medium or low, or by their WBS components. Another way of categorizing risks is to distinguish those requiring an immediate response from those that can wait for a response. ** Trends in qualitative analysis: As the project progresses and risk analysis is repeated, trends in the ranking and analysis of the risk may become apparent. These trends can allow the project manager and other risk experts to respond to the root cause and predicted trends to eliminate or respond to the risks within the project. ** Identification of risks requiring additional analysis: The risks categorized as high will probably need additional analysis, such as quantitative analysis. Some risks may demand immediate risk management based on the nature of the risks and the status of the project. v. What is a Decision Tree Method? How it is used for examining risks? ANSWER ; Each project risk is examined on its own merit by Sensitivity Analysis. All other risks in the project are set at a baseline value. Next, the individual risk is examined to determine how it may affect the success of the project. Determining which individual risks have the greatest impact on the project’s success is the goal of sensitivity analysis, followed by escalating the risk management processes on these risk events. Examining the Results of Quantitative Risk Analysis: Quantitative risk analysis is completed throughout the project as risks are identified and passed through qualitative analysis, either as project conditions change or on a preset schedule. The end results of quantitative risk analysis include the following: * Probabilistic analysis: “ The risks within the project allow the project manager or other experts to predict the likelihood of the project’s success. The project may be altered by the response to certain risks, which may increase costs and delay the project completion date. * A prioritized list of risks:” This list of quantified risks demonstrates those risks with the highest potential for endangering the project’s success. It includes the risks that have the greatest opportunities for the project. Each risk is identified along with its probability and impact. * Trends:” As the project moves towards completion, quantitative risk analysis may be repeated several times. In each round of analysis, trends in the identified risks may become visible. The trends in the risk can help the project team eliminate the root cause of the risks, reduce their probability, or control their impact. * Probability of costs and schedule objectives: “ Based on the identified risks, their impact, the probability of them occurring, forecasts for the project schedule and the project costs are created. The more negative risks that occur within a project, the greater the chance of delays and increased costs. Vi. Explain the term ‘risk response.’ ANSWER ; Risk response focuses on how to decrease the possibility of risks adversely affecting the project’s objectives and how to increase the likelihood of positive risks that can aid the project. Risks will increase or decrease based on the effectiveness of risk response planning. Risk response planning assigns responsibilities to people and groups close to the risk event. The responses to identified risks must be in balance with the risk itself. The cost and time invested in a risk must be met with the gains achieved from reducing the risk’s impact and probability. In other words, a million-dollar solution for a hundred-dollar problem is unacceptable. People assigned to the risk must have the authority to react to the project risk as planned. Usually, there will be several risk responses that may be viable for the risk; the best choice for the identified risk must be documented, agreed upon, and then followed through should the risk come to fruition . * Preparing for Risk Response ; To successfully prepare for risk response, the project manager, project team, and appropriate stakeholders will rely on several inputs—many of which stem from qualitative and quantitative risk analysis—such as the following: * The risk management plan  * Risk ranking  * A prioritized list of quantified risks  * A list of prioritized risks * The list of potential responses decided upon when risks were first identified * Any risk owners that have been identified, and a probabilistic analysis of the project * The probability of the project meeting the cost and schedule goals * Trends from qualitative and quantitative analysis * A listing of common causes of risks to address multiple risks with an achievable solution. * Creating Risk Responses : To respond to risks, the project team may employ several tools and techniques. To determine which category of risk response is most appropriate, each risk should be evaluated. When a category of risk response has been selected, the response must then be developed, documented, refined, and readied for use, if needed. Additionally, secondary responses may be selected for each risk. The purpose of risk response planning is to bring the overall risk of the project down to an acceptable level. Risk response planning must address any risks that have achieved an unacceptably high score. There are four categories of risk response: * Avoiding the Risk : Avoidance is simply avoiding the risk. This generally happens early in the project and can be accomplished in many different ways. Examples of avoidance include: * Using a proven methodology rather than a new approach.  * Changing the project plan to eliminate the risk. * Hiring additional project team members who have experience with the technology being employed by the project. * Clarifying project requirements to avoid discrepancies. * Mitigating the Risk : An effort to reduce the probability and/or impact of an identified risk in the project is called mitigating risks. Mitigation is carried out—based on the logic—before the risk occurs. Mitigation plans can be created in order that they might be implemented should an identified risk cross a given threshold. For example, a manufacturing project may have a mitigation plan to reduce the number of units created per hour should the equipment’s temperature cross a given threshold. The cost and time required to reduce or eliminate the risks is more cost-effective than repairing the damage caused by the risk. The risk event may still occur, but the cost and impact of the risk will both probably be very low. The reduction is the number of units per hour that it may cost the project in time. Additionally, the cost of extra labour to run the equipment longer because the machine is now operating at a slower pace may be attributed to the project. However, were the equipment to fail, the project would have to replace it and would be delayed for weeks while awaiting repairs. Examples of mitigation include: * Adding activities to the project to reduce the risk probability or impact * Completing more tests on the project work before implementation * Developing prototypes, simulations, and limited releases * Simplifying the processes within the project * Accepting the Risks : Risk acceptance is the process of simply accepting the risks because no other action is feasible, or the risks are deemed to be of small probability, impact, or both, and a formal response is not warranted. Active acceptance entails developing a contingency plan should the risk occur.Passive acceptance requires no action; the project team deals with the risks as they arise. A contingency plan is a predefined set of actions to be taken by the project team should the risk event occur. A contingency plan has also been called “a worst-case scenario” plan. Most risk acceptance policies rely on a contingency allowance for the project. A contingency allowance is an amount of money the project will probably need in the contingency reserve based on the impact, probability, and expected monetary value of a risk event. * Transferring the Risk: Transference is the process of transferring the risk (and the ownership of the risk) to a third party. The risk doesn’t disappear - it is simply someone else’s problem. Transference of a risk usually costs a premium for the third party to own and manage that risk. vii. What is ‘risk acceptance’? ANSWER ; * Accepting the Risks : Risk acceptance is the process of simply accepting the risks because no other action is feasible, or the risks are deemed to be of small probability, impact, or both, and a formal response is not warranted. Active acceptance entails developing a contingency plan should the risk occur.Passive acceptance requires no action; the project team deals with the risks as they arise. A contingency plan is a predefined set of actions to be taken by the project team should the risk event occur. A contingency plan has also been called “a worst-case scenario” plan. Most risk acceptance policies rely on a contingency allowance for the project. A contingency allowance is an amount of money the project will probably need in the contingency reserve based on the impact, probability, and expected monetary value of a risk event. * Transferring the Risk: Transference is the process of transferring the risk (and the ownership of the risk) to a third party. The risk doesn’t disappear - it is simply someone else’s problem. Transference of a risk usually costs a premium for the third party to own and manage that risk. viii. Give a few examples of risk transfer ANSWER ; Transference is the process of transferring the risk (and the ownership of the risk) to a third party. The risk doesn’t disappear - it is simply someone else’s problem. Transference of a risk usually costs a premium for the third party to own and manage that risk. Common examples of risk transference include: * Insurance * Fixed-priced contracts * Warrantees * Guarantees * Performance bonds 2. How can the effects of risks be mitigated? Give some examples. ANSWER ; An effort to reduce the probability and/or impact of an identified risk in the project is called mitigating risks. Mitigation is carried out—based on the logic—before the risk occurs. Mitigation plans can be created in order that they might be implemented should an identified risk cross a given threshold. For example, a manufacturing project may have a mitigation plan to reduce the number of units created per hour should the equipment’s temperature cross a given threshold. The cost and time required to reduce or eliminate the risks is more cost-effective than repairing the damage caused by the risk. The risk event may still occur, but the cost and impact of the risk will both probably be very low. The reduction is the number of units per hour that it may cost the project in time. Additionally, the cost of extra labour to run the equipment longer because the machine is now operating at a slower pace may be attributed to the project. However, were the equipment to fail, the project would have to replace it and would be delayed for weeks while awaiting repairs. Examples of mitigation include: * adding activities to the project to reduce the risk probability or impact. * Completing more tests on the project work before implementation. * Developing prototypes, simulations, and limited release * Simplifying the processes within the project 3. Discuss, in detail, the process of identifying project risks. ANSWER ; Armed with the inputs to risk identification, the project manager and the project team are prepared to begin identifying risks. Risk identification should be a planned, methodical approach. Should risk identification move in several different directions at once, some risks may be overlooked. A systematic, scientific approach is best. * Reviewing Project Documents : One of the first steps the project team should take is to review the project documentation, which includes project plan, scope, and other project files. This structure review takes a very broad look at the project plan, the scope, and the activities defined within the project. Constraints and assumptions should be reviewed, considered, and analyzed for risks. * Brainstorming the Project : The most common approach to risk identification is Brainstorming. This is usually completed by the project team as a whole to identify the risks within the project. A multidisciplinary team, hosted by a project facilitator, may also complete the brainstorming. This approach can include subject matter experts, project team members, customers, and other stakeholders in order to contribute to the risk identification process. The risks are identified in broad terms and posted before their characteristics are detailed. The identified risks are categorized and will pass through qualitative and quantitative risk analysis later. * Using the Delphi Technique : The Delphi Technique is an anonymous method of querying experts about foreseeable risks within a project, phase, or component of a project. There may be several rounds of anonymous discussions using the Delphi Technique—without fear of backlash or offending other participants in the process. The results of the survey are analyzed by a third party, organized, and then circulated to the experts. The Delphi Technique is completely anonymous and the goal is to gain consensus on project risks within the project. The anonymous nature of the process ensures that no one expert’s advice overtly influences the opinion of another participant. * Identifying Risks Through Interviews : Interviewing project stakeholders and subject-matter experts is an excellent approach to Identifying risks. The people responsible for risk identifications share the overall purpose of the project and the project’s WBS, and they probably have the same assumptions as the interviewee. Through questions and discussion, the interviewee shares his/her insights into what risks he/she perceives within the project. The goal of the process is to learn from the expert what risks may be hidden within the project, what insight the person has into the project work, and what risks this person has encountered on similar work.

For high grades use examples and illustrations where appropriate.

Please insert your completed assignment ( in word format) here:

Student Statement:

By submitting this assignment, I confirm that this is my own work.

| Student Signature | N.TUAZON | Date | July 23 2016 |
| --- | --- | --- | --- |

For Tutor / Assessor Use Only

| Total Marks |  |
| --- | --- |
| Marks Obtained |  |
| Percentage / Grade |  |