Assignment Cover Sheet

| Student Name: | Noel Catubig Tuazon |  |
| --- | --- | --- |
| Student Number: | 1762 |  |
| Course: | International Diploma in Project Management level 4 |  |
| Assignment NO: | 05 |  |

Marking Criteria:

We expect the learners to write minimum one well expressed point in three lines against each allocated mark. This means one needs to write 15 lines with 5 well expressed points to get high grades for a 5 marks question.

For high grades use examples and illustrations where appropriate.

Please insert your completed assignment ( in word format) here: Date: June 05 2016 ASSESMENT 5 1.) Give short answers for the following questions: i. What is the input for creating activity lists? ANSWER ; The activity list is an output of activity definition. It includes all of the activities to be performed within the project. The list must be in alignment with the project scope. Remember that the project scope is a description of all the work required, and only the work required, to complete the project. Since it includes only those actions needed to complete the project scope, the activity list is actually a further definition of the project scope. Creating the activity list relies on several completed documents, knowledge, and actions. The creation of the activity list uses the following as inputs to the process: WBS - serves as a major input in the creation of the activity list. The WBS is a deliverables- orientated collection of project components. It is not a collection of activities to create the deliverables. Scope statement - is a description of the work required, and only the work required, to complete the project. Historical information is proven information on which the project manager can rely to create activity lists. Expert judgment - Expert judgment allows experts to influence decisions in regard to the required work packages. Assumptions: - What assumptions have been identified for the project work? For example, consider the availability of resources, acceptable weather, and time allotted for completion of the project. Constraints: - What restrictions are imposed on the project manager and the project team? For example, is there a deadline for the project? Required quality metrics? A predetermined budget? These are examples of constraints. ii. What is the Arrow Diagramming Method and how does it work? ANSWER ; The Arrow Diagramming Method (ADM) approach to activity sequencing uses arrows to represent the activities. The arrows are “connected” to nodes. ADM only uses finish-to start relationships. Examining the Sequencing Outputs - There are many approaches to using activity sequencing: a project manager and the project team might use software programs, the approach can be done manually, or the team might carry out the scheduling manually and then transfer the schedule into a PMIS. Whichever method is selected, the project manager must remember four things: - Only the required work should be scheduled. - Activity sequencing is not the same as a schedule. - Finish-to-start relationships are the most common and preferred. - Scheduling comes after activity sequencing. iii. How does Project Network Diagram help in creating a flow of project work? ANSWER ; The flow of the project work can be visualized after the activity list has been put into sequential order. A project network diagram (PND) illustrates the relationship between the work packages and the flow of the project work. Assumptions about the activity sequence may reveal missing activities in the activity list during the creation of the network diagram. Just as the creation of the activity list may prompt the project team and the project manager to update the WBS, the creation of the network diagram may prompt the project team to update the activity lists. Although it may seem redundant to update the activities list illustrated in the project network diagram, it is essential documentation. The activity list, a reflection of the WBS, and the network diagram should support the project scope. A key stakeholder should be able to follow the logic of the WBS to the activity list, and from the activity list find all of the activities mapped in order. iv. What does the term ‘decomposition’ mean? Why are project activities decomposed? ANSWER - The WBS, the collection of deliverable-orientated components, must now be broken up into activities. Specifically, the work packages within the WBS must be decomposed into manageable work elements. What is the difference between decomposing the project deliverables and the project work? The elements in the WBS are deliverables; this process is concerned with the actions needed to create the deliverables. It is quite possible to create the WBS and the activity list in tandem. Try not to become too preoccupied with the timing of the activity list definition and the WBS. Simply put, the activity list defines the actions needed to create the deliverables; the WBS describes the components of the deliverables. A project manager might use a template from a previous project for this purpose. A template might include several elements to make a project manager’s life easier and the new project more successful: - Required resources and skills - Required actions to complete the project scope - Known risks - Outputs of the work - Required hours of duration for activities - Supporting details - Descriptions of the work packages Compiling the activity list comes next. The activity list also ensures that there is no extra work included in the project. Extra work costs time and money and defeats the project scope. The activities list comprises all of the work required to create the components within the WBS. v. How does a project manager decompose project components? ANSWER - The WBS, the collection of deliverable-orientated components, must now be broken up into activities. Specifically, the work packages within the WBS must be decomposed into manageable work elements. What is the difference between decomposing the project deliverables and the project work? The elements in the WBS are deliverables; this process is concerned with the actions needed to create the deliverables. It is quite possible to create the WBS and the activity list in tandem. Try not to become too preoccupied with the timing of the activity list definition and the WBS. Simply put, the activity list defines the actions needed to create the deliverables; the WBS describes the components of the deliverables. A project manager might use a template from a previous project for this purpose vi. Outline the factors that can affect a project’s length ANSWER - “ Considering the Resource Requirements “ - The project schedule will be affected by the identified resource requirements. Let us recall the difference between duration and effort. Duration refers to how long the activity will take, while effort is the labour applied to the task. For example, painting a building may take 80 hours to complete with two workers assigned to the job. With the addition of two more workers, the task will take only 40 hours. “ Considering the Resource Pool Availability “ - In a perfect world, all the resources required for a project would be available at the project manager’s command. In the real world, and in your PMP exam, the availability of project resources fluctuate due to the demands of other projects and on-going operations, vacations, sick days, personal lives, and more. The availability of the project pool must be evaluated. If certain activities require a worker with a highly specialized skill, these activities are resource-dependent. Should the worker be unavailable for the time frame of the required activity, one of several things must happen: - The activity must be moved in the schedule to a time when the resource is available. - The project manager must negotiate to make the resource available for the activity in the project schedule. - The project may incur additional costs by engaging other resources to complete the scheduled work. - The activity, and possibly the project, must wait for the resource to become available. “ Considering the Calendars “ There are two types of calendar that will affect the project: Resource calendar - The resource calendar controls when resources, such as project team members, consultants, and SMEs, are available to work on the project. It takes into account other commitments within the organization, vacations, or restrictions on contracted work, overtime issues, etc. Project calendar - This calendar shows when work is allowed on the project. For example, a project may require the project team to work nights and weekends in order to avoid disturbing the on-going operations of the organization during working hours. Additionally, the project calendar accounts for working hours, holidays, and work shifts covered by the project. Vii. Define the term ‘activity sequencing’. What are the inputs for activity sequencing? ANSWER ; There are many approaches to completing the activity sequencing. Perhaps the best approach is to undertake activity sequencing not as a solo activity but with the project team as a whole. The project manager must rely on the project team and the inputs to activity sequencing: “ Activity list” - The activity list, as we have just discussed, is the list of actions needed to complete the project deliverables. “ Product description” The product description is required since it may influence the sequence of events. For example, in construction, technology, or community planning (among other project types), the product description may include requirements that will logically affect the planning of activity sequencing. “ Mandatory dependencies “ These dependencies are the natural order of activities. These relationships are called hard logic. For example, you cannot begin building your house until your foundations are in place. “ External dependencies “ As the name implies, these are dependencies beyond the project’s control. Examples include delivery of equipment from a vendor, the deliverable of another project, or the decision of a lawsuit, committee, or expected new law. “ Discretionary dependencie “ :These dependencies are the preferred order of activities. Discretionary dependencies allow activities to take place in a preferred order because of best practices, conditions unique to the project work, or external events. Project managers should use these relationships at their “discretion” and document the logic behind the decision. For example, a painting project typically allows the primer and the paint to be applied within hours of each other. Due to the expected high humidity during the project, however, the entire building will be completely primed before the paint can be applied. These relationships are also known as soft logic, preferred logic, or preferential logic. “ Milestones “ Milestones must be considered and evaluated when sequencing events to ensure that all of the work needed to complete the milestones is included. viii. Apart from the duration of activities, which other factors can affect a project’s time ANSWER ; Creating honest estimates based on all the information provided is the best a project manager can do. No one will know the duration of the project until the schedule is finalized. The tasks are first identified, their duration is estimated, and then the sequencing of the activities takes place. These three activities are iterated as more information becomes available, and they are required to complete the project schedule and the estimated project duration. The project can move forward if the proposed schedule is acceptable. If the proposed schedule takes too long, the scheduler might use various strategies to compress the project. We will discuss the art of sequencing shortly. Activity duration estimates, like the activity list and the WBS, do not come from the project manager— they come from the people completing the work. Activity duration estimates may undergo progressive elaboration. In this section we will examine the approach to completing activity duration estimates, forming the basis of estimates, and allowing for activity list updates. Ix. What time - related risks could be involved in a project? ANSWER ; An example of a risk to the project is a delay by the vendor in sending the equipment needed to complete the project. If a risk occurs, the response to this risk may be to secure an alternative vendor who charges slightly more for the same equipment but has it in stock. The original vendor’s delay in sending the equipment may throw the project off schedule, and the additional time needed to find, purchase and ship the required equipment may also add extra time to the project. 2. You are the project manager for a large construction project. The project objective is to construct a set of outbuildings to house the Olympic support team that will be arriving in your city 15 months from the project’s start date. You’ve been given a budget of $18 million to complete this project. Resources are easily attained. Which of the triple constraints is the primary constraint for this project? ANSWER ; a. Time, because the date cannot be moved 3. Explain Precedence Diagramming Methods of arranging project work. ANSWER ; The most common method of arranging the project work visually is the Precedence Diagramming Method (PDM). The PDM puts the activities in boxes, called nodes, and connects the boxes with arrows. The arrows represent the relationships and the dependencies of the work packages. The following illustration shows a simple network diagram using PDM. “ Start-to-start (SS):” This relationship means that Task A must start before Task B can start. This relationship allows both activities to occur in tandem. For example, a crew of painters is painting a house. Task A is to scrape the flecking paint off the house and Task B is to prime the house. The workers scraping the house must start before the other workers can begin priming the house. Not all of the scraping necessarily needs to be completed before the priming can start - just some of it. “ Finish-to-start (FS) “ This relationship means that Task A must be completed before Task B can begin. This is the most common relationship. The foundation must be set before the framing can begin, for example. “ Finish-to-finish (FF) “ This relationship means that Task A must be completed before Task B is completed. Although this is not always the case, ideally, two tasks must finish at exactly the same time. For example, two teams of electricians may be working together to install new telephone cables throughout a building by Monday morning. Team A is pulling the cables to each office. Team B is connecting the cables to wall jacks and connecting the telephones. Team A must pull the cables to the office in order that Team B might complete their activities. The activities need to be completed at nearly the same time, by Monday morning, to ensure that the new phones are functional. “ Start-to-finish (SF) “ This relationship is also known as just-in-time (JIT) scheduling. It is unusual and is rarely used. It requires that Task A be started in order that Task B might finish. Such relationships may be encountered in construction and manufacturing. An example is the construction of a shoe store. The end of the construction is imminent, but the exact date is no known. The owner of the shoe store doesn’t want to order the shoe inventory until the construction is nearly complete. The start of the construction tasks dictates when the shoe inventory is ordered..

Student Statement:

By submitting this assignment, I confirm that this is my own work.

| Student Signature | N.TUAZON | Date | June 05 2016 |
| --- | --- | --- | --- |

For Tutor / Assessor Use Only

| Total Marks |  |
| --- | --- |
| Marks Obtained |  |
| Percentage / Grade |  |