Assignment Cover Sheet

| Student Name: | Rebecca Angle |
| --- | --- |
| Student Number: | 12145 |
| Course: | Certificate in Event Management Level 1 |
| Assignment NO: | Unit 1 |

Marking Criteria:

We expect the learners to write minimum one well expressed point in three lines against each allocated mark. This means one needs to write 15 lines with 5 well expressed points to get high grades for a 5 marks question.

For high grades use examples and illustrations where appropriate.

Student Statement:

By submitting this assignment, I confirm that this is my own work.

| Student Signature | Rebecca Angle | Date | 20.10.17 |
| --- | --- | --- | --- |

For Tutor / Assessor Use Only

| Total Marks |  |
| --- | --- |
| Marks Obtained |  |
| Percentage / Grade |  |

| Student Name: | Rebecca Angle |
| --- | --- |
| Student Number: | 12145 |
| Assignment Number: | 1 |
| Page Number: | 1 |

- MAIN DUTIES AND RESPONSIBILITIES OF AN EVENT PLANNER

To ensure an event is successful, it is imperative that it is carefully planned, organised and completed within budget and timescale, taking into consideration the following points:

- Client liaison to establish exact requirements

- Carry out market research/fact finding to produce an ‘Event Plan/Schedule’

- Provide regular client feedback to confirm client satisfaction

- Negotiate with suppliers to comply with budget restraints

- Organisation of event to ensure customer satisfaction

- Utilisation of problem solving skills to handle any issues

- Promote the event to ensure maximum publicity/client satisfaction.

- MAIN TASKS

- Establishment of  client requirements to include; budget, timescale, venue, number of attendees, dietary requirements, venue  access  and any other client specifications, for example, special guests, arranging overnight accommodation,  ‘housekeeping’ issues, for example, setting up/clearing up and staff assignment of key responsibilities, for example, organising the illumination of the venue and  first aid requirements

- Ensure bank facilities agreed and set up in order to pay invoices for event

- Conduct market research/information gathering/negotiation with suppliers

- Provide regular feedback to client to ensure satisfaction

- Confirm venue, catering, entertainment, transportation, invitee list, equipment, promotional material, special requirements, for example, disabled access required

- Ensure all compliance issues are in place in respect of public liability insurance and health and safety

- Interview and book staff if not provided by venue, detailing their role for the event

- Carry out promotion and marketing, for example, produce flyers or advertise in company newsletter or external media such as local radio or television, internet

- Produce and send out invitations

| Student Name: | Rebecca Angle |
| --- | --- |
| Student Number: | 12145 |
| Assignment Number: | 1 |
| Page Number: | 2 |

- Coordinate all staff activity during the event, establishing staff accountability

- Proactively deal with any problem or issues, including emergencies

- Obtain client feedback to ensure satisfaction and repeat business

If the client has a specific marketing strategy, this should be adhered to and an ‘Event Schedule’ produced to contain all the above relevant information, for example, a list of invitees/attendees.

- THE 5 ‘Ws’ IN EVENT CREATION/IMPORTANCE WHEN EVENT PLANNING

The 5 Ws are; Who, What, Where, Why and When.

- ‘Who’ – identify who the target market is, that is, the guest list, establishing any special needs, for example, dietary, physical disabilities, are VIPs required

- ‘What’ – establish event objectives, for example, is the event to increase brand awareness

- ‘Where’ – establish best venue(s), taking parking requirements into consideration and set-up requirements, for example, if attendees are arriving by train or being dropped at the venue, parking may not be an important issue

- ‘Why’ – understand what is the benefit of the event for the attendees, for example, if the attendees are speculative invitees and unknown to the client, there needs to be a benefit or interest for them, for example, a VIP speaker or celebrity in attendance, whom the audience can relate to and admire

- ‘When’ – establish if the event is a ‘one-off’ or a regular event, for example, in the instance of a one-off event to promote the re-opening of a business (care home), it would be crucial to build up a database of future potential customers to invite to the event.  This would give the care home the opportunity of having the potential customers on site in order to view the changes to the venue and establish interest in the product for a future date.

| Student Name: | Rebecca Angle |
| --- | --- |
| Student Number: | 12145 |
| Assignment Number: | 1 |
| Page Number: | 3 |

The benefit of setting up an event plan, if followed meticulously  will ensure that no point is overlooked or forgotten, for example, if the event planner is absent for any reason, all the information is logged in the ‘plan’ for someone else to take over.  The ‘plan’ should be easy to understand, preferably organised in different labelled sections with clear headings, for example,’Event Contacts’.

- HOW SHOULD AN EVENT PLANNER EVALUATE A VENUE TO ENSURE IT SERVES THE EVENT’S REQUIREMENTS

There are a number of considerations, as follows:

In the first instance, the type of venue should be decided, that is, either a hotel which offers overnight accommodation, in-house catering and staff or a public venue or even a room within the client’s own premises may be more suitable if, for example, the client wants to promote their own products or services by hosting the event in-house.   If the latter option chosen, the event planner would need to research provision of extra resources, such as, catering and staffing.  Once a short list of potential venues has been drawn up, they should then be viewed and if suitable, exact requirements discussed with the venue contact.  The following points need to be taken into consideration:

- Review the facilities, utilities and venue resources, for example, do they have all the ICT equipment such as TV, projector, telephones, lighting options, for example, is the room well lit and a  suitable areas for promotional material to be displayed, is there a central reception desk or would this need to be done by the event planner within the allocated room, what in-house business services are provided, such as in-house staff  to provide administrative/reception support, for example, photocopying may be required on the day

- Establish what room options are available to accommodate different numbers of people and what layout options would be provided – if a hotel venue required, establish if all attendees can be accommodated overnight if required

- Discuss catering options with venue contact (if a public venue)  to establish if they can provide the service required, if not, outside caterers would need to be employed

- Carry out a Risk Assessment of venue, for example, to assess adequate emergency exits, health and safety issues such as trip hazards on fraying carpets, signage and suitability of access for people with additional needs or requirements, for example, providing extra space for a carer or guide dog

| Student Name: | Rebecca Angle |
| --- | --- |
| Student Number: | 12145 |
| Assignment Number: | 1 |
| Page Number: | 4 |

- Assess the outside area and the approach to the venue should be considered, as if the terrain is difficult, this may cause problems for attendees, for example, pushing a wheelchair over grass could prove difficult for a carer

- Confirm the number of parking bays available for the event and ease of parking, for example, is the car park within the grounds of the venue or nearby

- Verify with the venue contact their documentation in respect of their legal responsibilities, for example, sight of their public liability insurance in the event of an accident/claim

- Before deciding on venue, ensure all the above castings/quotations are within the client’s budget!

- AN EVENT PLANNER IS A PERSON WITH APPROPRIATE SKILLS FOR MAKING TIMELY DECISIONS - DISCUSS

There are a number of crucial skills required:

- Ability to multi-task – this role requires a person who can remain focussed and calm, under pressure whilst still able to perform their duties to the best of their ability, for example, a key speaker cancels their slot the day before the event – the planner must re-prioritise their schedule to find a replacement at short notice.  This may involve paying a higher fee to a new speaker and the effect of this will be a change in the budget which may need to be agreed with the client if the overall budget has been met already

- Resourcefulness – this is something that plays an important part in the role.  If a change to the agreed plan occurs as in the example above, the planner may need to ‘network’ all contacts in order to satisfy the remit, for example , finding a replacement speaker at short notice

- Negotiator – this skill is useful when budgets are tight and the planner needs to have a convincing argument in order to successfully persuade a supplier/contractor etc that they are working within budgetary requirements, for example, negotiating with a celebrity speaker’s agent over their fee

| Student Name: | Rebecca Angle |
| --- | --- |
| Student Number: | 12145 |
| Assignment Number: | 1 |
| Page Number: | 5 |

- Organisational skills to include excellent social interaction is required in order to ensure that the event process is followed through and no point overlooked, putting in place contingency plans, such as, details of other event providers with availability, should the venue be cancelled at late notice

- Time Management – this is key in ensuring plans are in place within certain timescales to avoid delays and budget increases, for example, leaving the booking of a guest speaker until the last minute, may mean the speaker is already booked or will charge a fee increase

- Excellent ICT – the planner will need to assemble a database of invitees/attendees, contractors, suppliers etc. together with production of marketing information

- Attention to detail – it will be important to proof read any marketing material to ensure no errors in print before distribution

- Communication – a very important skill as the planner needs to be able to clearly communicate requirements and deal with a variety of people ensuring no misunderstandings, in addition to analysing supplier and contractor quotations

- Marketing/Public Relations – event planners will need to have commercial awareness, for example, if the event has any political connections, all necessary government regulations will need to be adhered to

- Research – this needs carefully consideration to ensure the client is presented with all options in respect of the project, for example, choice of venues, budgetary costings

- Creativity -  may be required, for example, to produce an eye-catching flyer.

‘References’:

N/A